## Public Relations Team
Role: | Name | Phone | Email
PRM | Mary Hoftiezer | 720-301-6591 | mhoftiezer.prm@d26leaders.org
Webmaster | Greg Harris | 909-437-1133 | Webmaster@D26Leaders.org
Web Designer | Lou Watson | 8014403863 | lcs0618@gmail.com
Newsletter Editor | None yet
Social Media Coordinator | None yet
Public Relations | Mary Hoftiezer | 720-301-6591 | mhoftiezer.prm@d26leaders.org
Graphic Designer | None yet
District Administration Manager | Deb Horowitz
Podcaster | None yet
Blogger | None yet
Toastmasters International Branding |  |  | brand@toastmasters.org
Available Communication Methods: | Location | Coordinator
District Website | https://www.d26toastmasters.org/
District Facebook Page | https://www.facebook.com/District26Toastmasters
District Facebook Members Group | https://www.facebook.com/groups/d26toastmastersmembersgroup
District Twitter Account | https://twitter.com/D26Toastmasters?s=20
District LinkedIn Group | https://www.linkedin.com/company/390685/admin/
Bulk Email System (i.e. Constant Contact, etc.) | Constant Contact
Directed Email through Area Directors |  | District Administration Manager
News Release
Audience:
All Members
Club Officers
District Council
Division Council
Area Council
District Executive Committee
External

## Resources
Online Resources | Link
Let the World Know Handbook | https://www.toastmasters.org/~/media/4961f7be4b244a12a39426d0c9193cd1.ashx
Brand Manual | https://www.toastmasters.org/Resources/Resource-Library?t=brand%20manual
Public Relations Resources | https://www.toastmasters.org/Leadership-Central/Club-Officer-Tools/Club-Officer-Roles/Public-Relations
Logo, Images, and Templates | https://www.toastmasters.org/resources/logos-images-and-templates
Sample News Releases | https://www.toastmasters.org/leadership-central/club-officer-tools/club-officer-roles/public-relations/sample-news-releases
Toastmasters Media Center | https://mediacenter.toastmasters.org/

## Internal Communications
Internal Communications
Description | Audience | Communications Method | Date | % Complete | Owner | Approver | Approval Lead Time | Tasks
District Appointments | All Members | 1. District Website 2. District Facebook Members Group 3. Email to All Members | 2023-07-01 | 0% | DD | DD | 2 days | 1. Create email listing all appointed DEC positions 2. Send to PR team for distribution
District Calendar | All Members | 1. District Website 2. District Facebook Members Group 3. Email to All Members | 2032-07-22 | 0% | DD | DD | 2 days | 1. Finalize District Calendar 2. Send to PR team for distribution
Smedley Membership Campaign | Club Officers | 1. District Facebook Members Group 2. Email to Club Officers | 2023-08-01 | 0% | CGD | DD | 2 days | 1. Create email promoting Smedley Membership Award 2. Get DD approval 3. Send to PR team for distribution
HOF | All members | 1. District Facebook Members Group | 2023-08-03 | 100% | PRM | DD | 2 days | 1. Create FB post
Followup to July 29 COT | Specific Club Officers who did not attend most recent COT | 1. Email to specific club officers | 2023-08-06 |  | PQD/PRM |  |  | 1. Create email to specific club officers who did not attend recent COT.
Club Officer Training | Club Officers | 1. District website 2. District Facebook Members Group | 2023-08-25 | 100% | PRM | DD | 2 days | 1. Create Canva presentation with awards
HOF Awards | All members | 1. District website 2. District Facebook Members Group | 2023-08-29 | 100% | PRM |  | 2 days | 1. Create Canva presentation with awards
Triple Crown Awards | All members | 1. District website 2. District Facebook Members Group |  | 100% | PRM |  | 2 days | 1. Create Canva presentation with awards
LevelUp Pathways Awards | All members | 1. District website 2. District Facebook Members Group |  | 100% | PRM |  | 3 days | 1. Create Canva presentation with awards
Club Coach Club Mentor | All members | 1. District website 2. District Facebook Members Group | 2023-09-04 | 1% | PRM CGD | DD | 2 days | 1. Use Ruth's post and get on social media
Club Coach Training | All members | 1. District website 2. District Facebook Members Group | 2023-09-08 | 0% | PRM CGD | DD | 2 days | 1. Use Ruth's post and get on social media
Tuesday's Toastmasters Tips | Club Officers | 1. District website 2. District FB Members Group 3. IG 4. Twitter 5. LinkedIn | 2023-09-05 |  | PRM |  | 1 week | 1. Create template 2. Record video, podcast, etc. 3. Add to Canva. 4. Post to Social Media
Spotlight on TM
Talk Up Toastmasters! | Club Officers | 1. District Facebook Members Group 2. Email to Club Officers | 2024-01-25 | 0% | CGD | DD | 2 days | 1. Create email promoting Smedley Award 2. Get DD approval 3. Send to PR team for distribution
Beat the Clock | Club Officers | 1. District Facebook Members Group 2. Email to Club Officers | 2024-04-25 | 0% | CGD | DD | 2 days | 1. Create email promoting Smedley Award 2. Get DD approval 3. Send to PR team for distribution
District Newsletter | All Members | 1. District Website 2. District Facebook Members Group 3. Email to All Members | determine schedule | 0% | Newsletter Editor | DD | 2 days | 1. Collect Articles from Members and District Officers 2. Compile into Newsletter 3. Send to DD for Review 4. Send to PR team for distribution
Member Spotlight | All Members | 1. District Facebook Members Group | monthly | 0% | PRM | DD | 2 days | 1. Determine member for spotlight 2. Get photos 3. Interview member 4. Write spotlight article 5. Send to member for review 6. Send to DD for approval 7. Send to PR team for distribution
DEC Meeting (each) | DEC Members | 1. Email to DEC Members | 2 weeks' prior (per Protocol 7.1.4 District Executive Committee Meetings | 0% | Admin Manager | DD | 2 days | 1. Finalize Agenda 2. Send Email, Agenda, and Items Requiring a Vote
Area Council Meeting | Area Council | 1. Email to Area Council Members | 30 days' prior | 0% | Area Director | Area Director | NA | 1. Create Email 2. Send Email to Area Council Members
Division Social Event | Division Council | 1. Division Council Members | 2 weeks' prior | 0% | Event Coordinator | Division Director | 2 days | 1. Create Email 2. Send Email to Division Council Members
Note on A14: ====== ID#AAAA4rRtalk Mary Hoftiezer (2023-09-06 02:49:28) Refer to Tuesday's TM Tip Tab

## Spotlight on TM
Week # | Week Date | Topic | Author | Due by date | Post on date

## Tuesdays TM Tip
Week # | Week Date | Topic | Author | Due by date | Post on date
1 | 2023-10-01 | Tuesday's TM Tip: Power Up Your Role as President |  | 2023-09-29 | 2023-10-03
2 | 2023-10-08 | TTT: VPE Extroardinare |  | 2023-10-06 | 2023-10-10
3 | 2023-10-15 | TTT: VPM Magnificent |  | 2023-10-13 | 2023-10-17
4 | 2023-10-22 | TTT: SAA |  | 2023-10-20 | 2023-10-24
5 | 2023-10-29 | TTT: VPPR Get the word out |  | 2023-10-27 | 2023-10-31
6 | 2023-11-05 | TTT:Secretary |  | 2023-11-03 | 2023-11-07
7 | 2023-11-12 | TTT: Treasurer |  | 2023-11-10 | 2023-11-14
8 | 2023-11-19 | TTT: Pathways Passageway |  | 2023-11-17 | 2023-11-21
9 | 2023-11-26 | TTT: Talking Turkey at Toastmasters |  | 2023-11-24 | 2023-11-28
10 | 2023-12-03 | TTT: Holiday Talk Hassle or |  | 2023-12-01 | 2023-12-05
11 | 2023-12-10 | TTT: Mid year goals |  | 2023-12-08 | 2023-12-12
12 | 2023-12-17 | TTT: |  | 2023-12-15 | 2023-12-19
13 | 2023-12-24 | TTT: |  | 2023-12-22 | 2023-12-26
14 | 2023-12-31
15

## External Communications
External Communications
Description | Audience | Communications Method | Date | (% Complete) | Owner | Approver | Approval Lead Time | Tasks
Announcement of District Director | External | 1. News Release 2. District Facebook Page | 2023-07-01 | 0% | PRM | DD | 2 days | 1. Write News Release announcing new DD 2. Send to PR team for distribution
Newspaper Ad in Arvada | External | 1. Newspaper Ad | 2023-07-24
Email to DEC members | External | 1. Email | 2023-07-24
District Calendar to All Clubs | External | 1. Email | 2023-07-24
Train the Trainer | External | 1. Social Media Post | 2023-07-27 | 100% | PRM |  |  | 1. Create on Canva
Smedley Award | External | 1. Email | 2023-08-01 |  |  | DD | 2 days
Glenn West Announcement | External | 1. Email | 2023-08-01
Monthly Newsletter | External | 1. Email | 2023-08-01
Announcement of Communications & Leadership Award | External | 1. News Release 2. District Facebook Page | 2024-04-01 | 0% | PRM | DD | 2 days | 1. Write News Release announcing C&L Award 2. Approval by Recipient and DD 3. Send to PR team for distribution
Announce Keynote Speaker for Conference | External | 1. News Release 2. District Facebook Page | 2024-03-01 | 0% | PRM | DD | 2 days | 1. Write News Release announcing Keynote Speaker 2. Approval by Speaker and DD 3. Send to PR team for distribution
Announce Visit by ID/IO | External | 1. News Release 2. District Facebook Page | 2024-03-01 | 0% | PRM and WHQ | DD | 2 days | 1. Write News Release announcing ID/IO Visist 2. Approval by ID/IO, WHQ and DD 3. Send to PR team for distribution
Announce International Speech Contest Winner | External | 1. News Release 2. District Facebook Page | 2024-06-01 | 0% | PRM | DD | 2 days | 1. Write News Release announcing ISC Winner 2. Approval by ISC Winner and DD 3. Send to PR team for distribution
Community Club Launch Meeting | External All Members | 1. News Release 2. District Facebook Page 3. District Facebook Members Group | as needed | 0% | CGD | DD | 2 days | 1. Write News Release announcing new Club 2. Approval by DD 3. Send to PR team for Distribution
New Club Announcement | External All Members | 1. News Release 2. District Facebook Page 3. District Facebook Members Group | as needed | 0% | CGD | DD | 2 days | 1. Write News Release announcing new Club 2. Approval by DD 3. Send to PR team for Distribution
Radio Interviews
Local Television Channel Interviews

## District Council Meetings
100%
Virtual District Council Meeting | Date |  | Time |  |  | Online URL:
Description | Audience | Communications Method | Date | (% Complete) | Owner | Approver | Approval Lead Time | Tasks
Announce District Council Meeting | District Council Members | 1. Bulk Email 2. Directed Email via Area Directors 3. District Facebook Members Group 4. District Website | 30 days' prior (per Protocol 7.1.5 - District Council Meetings | 0% | Admin Manager | DD | 2 Days | 1. Determine Council Date 2. Setup Virtual Council Method - obtain URL 3. Determine Voting Method 4. Create Communication 5. Send to PR team for Distribution
Distribute agenda and all items requiring a vote | District Council Members | 1. Bulk Email 2. Directed Email via Area Directors 3. District Facebook Members Group 4. District Website | 14 days' prior (per Protocol 7.1.5 - District Council Meetings | 0% | Admin Manager | DD | 2 Days | 1. Complete agenda 2. Create PDF of DEC Approved Budget 3. Create PDF of District Appointments 4. Create PDF of any other items requiring a vote 5. Get copy of Audit Committee Report 6. Create communication, including instructions on how to vote during or after meeting 7. Approval of DD 8. Send to PR team for Distribution
Annual Business Meeting | Date |  | Time |  |  | Location
Description | Audience | Communications Method | Date | (% Complete) | Owner | Approver | Approval Lead Time | Tasks
Announce Annual Business Meeting | District Council Members | 1. Bulk Email 2. Directed Email via Area Directors 3. District Facebook Members Group 4. District Website | 30 days' prior (per Protocol 7.1.5 - District Council Meetings | 0% | Admin Manager | DD | 2 Days | 1. Determine Council Date 2. Determine Voting Method 3. Create Communication 4. Send to PR team for Distribution
Distribute agenda and all items requiring a vote | District Council Members | 1. Bulk Email 2. Directed Email via Area Directors 3. District Facebook Members Group 4. District Website | 14 days' prior (per Protocol 7.1.5 - District Council Meetings | 0% | Admin Manager | DD | 2 Days | 1. Complete agenda 2. Create PDF of District Leadership Committee Report 3. Create PDF of District Realignment Committee Report 4. Create PDF of any other items requiring a vote 5. Attach copy of Audit Committee Report for First Half of Year 6. Attach copy of the District Proxy Form 7. Create communication 8. Approval of DD 9. Send to PR team for Distribution

## Social Media Posting
Description | FB Member Page + Instagram | D26 FB Page + Twitter (Sun, Wed, Fri) | Linkedin (Mon, Wed, Fri) | Date | Day of the week
Coach Mentor Training | X | X | X | 2023-09-04 | Monday